## Sheet1
November
Developer | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Total HRS
Adam Abernathy | [7 empty] | 1 | [6 empty] | 5 |  |  |  | 6
Michael Talaga | [6 empty] | 3.5 | [5 empty] | 0.5 | 0.75 | 1 | 1.5 |  |  | 7.25
Morgan Marino | 0.5 | 2 |  | 0.5 |  |  |  | 1 |  |  | 1.5 | 0.5 |  | 0.5 | 1 |  |  |  | 7.5
Divya Shakamuri | [7 empty] | 0.5 |  |  |  | 2 | 2 |  | 1 | 0.5 |  |  | 6
Mason Otto | 0.5 |  |  | 2 | 2 |  |  |  |  | 2.5 | 2 |  |  |  | 1 |  |  |  | 10
36.75
Estimate of person-hours: 40
Reasoning: The reason we picked 40 hours is because it's approximately where we've been landing with our hours since Project 1. In Project 1 and 2, we predicted 40 hours, but in Project 3, we predicted 30 hours and was way below what it actually was. We are hoping 40 hours is enough time to finish our project, clean it, and create a video, but we won't overdo or strain ourselves and our busy schedules.